## Sheet1
Manual Test Executioon Summary
|  |  | Test Status | Test Count
|  |  | PASS | 81
|  |  | FAIL | 65
|  |  | WIP | 115
|  |  | BLOCKED | 50
|  |  | UNEXECUTED | 0
|  |  | Total | 311
ExecutionId | CycleName | Issue Key | Test Summary | Labels | Project | Component | Version | Priority | Assigned To | Executed By | Executed On | Execution Status | Comment | Execution Defects | Creation Date | Step | Test Data | Expected Result | Step Result | Comments
96021 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18581 | UX Design - UI Design Considerations | Sample_GRAPH , TC_L1 , UX_DESIGN | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-05-08 | WIP |  |  | 2017-04-26
96019 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18582 | UX Design - Layout Feature - Vertical pane for customized filter fields | Sample_GRAPH , TC_L2 , UX_DESIGN | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-26 | PASS |  |  | 2017-04-26
96018 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18583 | UX Design - Layout Feature - Vertical pane - Verify Alignment of filters | Sample_GRAPH , TC_L3 , UX_DESIGN , VER_PANE | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-26 | FAIL |  |  | 2017-04-26 | Check whether the captions inside buttons are displayed properly |  | Captions inside buttons should be displayed properly | FAIL
[16 empty] | Alignment of buttons |  |  | FAIL | Variance button is not aligned properly with other advanced option buttons
[16 empty] | Check whether the text boxes are align properly |  | Text boxes should be align properly | FAIL | Instrument filter filed text box and Overlay Instrument filter filed text box are not aligned.
Valiance Text box is not aligned properly with other advanced filter field text boxes.
[16 empty] | Check whether Tool tip information available for relevent elements |  | Tool tips should be available for relevant items | BLOCKED | Need to clarify with BS. Raised a sub task- Sample-19569
96046 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18594 | UX Design - Layout Feature - Generic display pane should be available for visualization of Bid and Offer | Sample_GRAPH , TC_L2 , UX_DESIGN | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-26 | PASS |  |  | 2017-04-26
95960 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18595 | UX Design - Layout Feature - Labels pane should be available to hold labels of selected instruments | Sample_GRAPH , TC_L2 , UX_DESIGN | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-26 | PASS |  |  | 2017-04-26
95962 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18596 | UX Design - Layout Feature - Analytics pane should be attached to the bottom of the BOG for on demand analytics and statistics | Sample_GRAPH , TC_L2 , UX_DESIGN | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-26 | PASS |  |  | 2017-04-26
95971 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18602 | UX Design - Specific features of UI design | Sample_GRAPH , TC_L1 , UX_DESIGN | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-05-08 | WIP |  |  | 2017-04-26
95970 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18603 | UX Design - Specific features of UI design - Ability to collapse the the analytics pane in downward direction on demand by dragging the splitter | Sample_GRAPH , TC_L2 , UX_DESIGN | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-26 | PASS |  |  | 2017-04-26
95975 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18604 | UX Design - Specific features of UI design - BOG should be automatically re-sized to fit the window when other panes are collapsed | Sample_GRAPH , TC_L2 , UX_DESIGN | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-26 | PASS |  |  | 2017-04-26
95976 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18605 | UX Design - Specific features of UI design - The main BOG window should be dock-able in the main workstation as a tab | Sample_GRAPH , TC_L2 , UX_DESIGN | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-26 | PASS |  |  | 2017-04-26
95973 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18606 | Functional Features - Graph Axis | FUNCTIONAL_FEATURES , GAX , Sample_GRAPH , TC_L1 | Sample Project Client |  | Sample 5.0.0.0.i10 | Emergency | Indika Deshapriya | Indika Deshapriya | 2017-05-08 | WIP |  |  | 2017-04-26
95978 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18607 | Functional Features - Graph Axis - Graph price series availability in vertical left side Y axis | FUNCTIONAL_FEATURES , GAX , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | Emergency | Indika Deshapriya | Indika Deshapriya | 2017-04-26 | PASS |  |  | 2017-04-26 | Check graph price series availability in vertical left side Y axis |  | Graph price series is availabile in vertical left side Y axis | UNEXECUTED
[16 empty] | Check whether the price is up to two decimal points |  | The price should be up to two decimal points | UNEXECUTED
95984 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18608 | Functional Features - Graph Axis - All axis should automatically scaled based on user filtering criteria | FUNCTIONAL_FEATURES , GAX , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | Emergency | Indika Deshapriya | Indika Deshapriya | 2017-04-26 | PASS |  |  | 2017-04-26
96013 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18610 | Functional Features - Graph axis - Graph volume series availability in vertical right side Y axis as default series | FUNCTIONAL_FEATURES , GAX , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | Emergency | Indika Deshapriya | Indika Deshapriya | 2017-04-26 | PASS |  |  | 2017-04-26 | Check graph volume series availability in vertical right side Y axis as default series |  | Graph Volume series is availabile in vertical right side Y axis as default series | UNEXECUTED
[16 empty] | Check whether the volume is up to two decimal points |  | The volume should be up to two decimal points | UNEXECUTED
96027 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18614 | Functional Features - Querying Functionality | FUNCTIONAL_FEATURES , QUERY , Sample_GRAPH , TC_L1 | Sample Project Client |  | Sample 5.0.0.0.i10 | Emergency | Indika Deshapriya | Indika Deshapriya | 2017-05-08 | WIP |  |  | 2017-04-26
96025 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18615 | Functional Features - Querying Functionality - Ability to query for a symbol via user text input querying | FUNCTIONAL_FEATURES , QUERY , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | Emergency | Indika Deshapriya | Indika Deshapriya | 2017-05-12 | PASS |  | Sample-19561 | 2017-04-26 | Type a instrument name in the query field | INSCR87_01 | Typed instrument details should be queried and displayed | PASS
Press query button
96042 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18617 | Functional Features - Querying Functionality - Check maximum number of days for the query period | FUNCTIONAL_FEATURES , QUERY , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | Emergency | Indika Deshapriya | Indika Deshapriya | 2017-05-12 | PASS |  |  | 2017-04-26
96039 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18618 | Functional Features - Querying Functionality - Availability of Instrument filter in filters pane | FUNCTIONAL_FEATURES , QUERY , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | Emergency | Indika Deshapriya | Indika Deshapriya | 2017-04-26 | PASS |  |  | 2017-04-26 | Check whether the Symbol filter is available in filters pane |  | The Symbol filter is available in filters pane | PASS
96060 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18619 | Functional Features - Querying Functionality - Availability of Date (From/To) filter in filters pane | FUNCTIONAL_FEATURES , QUERY , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | Emergency | Indika Deshapriya | Indika Deshapriya | 2017-04-26 | PASS |  |  | 2017-04-26 | Check whether the Date (From/To) filter is available in filters pane |  | Date (From/To) filter is available in filters pane | UNEXECUTED
96064 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18620 | Functional Features - Querying Functionality - Availability of Time (From/To) filter in filters pane | FUNCTIONAL_FEATURES , QUERY , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | Emergency | Indika Deshapriya | Indika Deshapriya | 2017-04-26 | PASS |  |  | 2017-04-26 | Check whether the Time(From/To) filter is available in filters pane |  | Time(From/To) filter is available in filters pane | PASS
96058 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18622 | Functional Features - Querying Functionality - The filter fields should facilitate appropriate input methods depending on the data type of the respective field | FUNCTIONAL_FEATURES , QUERY , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | Emergency | Indika Deshapriya | Indika Deshapriya | 2017-05-12 | WIP |  |  | 2017-04-26
95956 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18624 | Functional Features - Graph axis - Graph turnover/consideration series availability in vertical right side Y axis on demand | FUNCTIONAL_FEATURES , GAX , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | Emergency | Indika Deshapriya | Indika Deshapriya | 2017-05-08 | FAIL |  |  | 2017-04-26 | Query for an instrument |  |  | PASS
[16 empty] | Try to change into the turnover series by clicking upper right corner of volume series |  | Turnover series should appear in vertical right side Y axis | FAIL
[16 empty] | Try to change into the Consideration series by clicking upper right corner of volume series |  | Consideration series should appear in vertical right side Y axis | FAIL
95996 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18627 | Functional Features - Querying Functionality - When querying for a symbol, the series to be drawn should be able to select from the list menu next to the Instrument ID query field using checkboxes | FUNCTIONAL_FEATURES , QUERY , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | Emergency | Indika Deshapriya | Indika Deshapriya | 2017-04-26 | FAIL |  |  | 2017-04-26 | Query for a symbol |  |  | PASS
The series to be drawn should be able to select from the list menu next to the Instrument ID query field using checkboxes
[16 empty] | *Query for a symbol |  | Selected series should be drawn | FAIL
*Select the series to be drawn from the list menu next to the Instrument ID query field
95995 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18628 | Functional Features - Querying Functionality - Name of the symbol should be added as a label (Instrument label) on top of the graph, once the Sample Graph is drawn | FUNCTIONAL_FEATURES , QUERY , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | Emergency | Indika Deshapriya | Indika Deshapriya | 2017-04-26 | PASS |  |  | 2017-04-26
96010 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18630 | Functional Features - Querying Functionality - When the instrument label is selected it should list down all user selected series in a menu | FUNCTIONAL_FEATURES , QUERY , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | Emergency | Indika Deshapriya | Indika Deshapriya | 2017-04-26 | BLOCKED | As spec point is unclear |  | 2017-04-26
96020 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18631 | Functional Features - Querying Functionality - Ability to enable/disable any series from the toggle options in series menu derived by selecting the instrument label | FUNCTIONAL_FEATURES , QUERY , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | Emergency | Indika Deshapriya | Indika Deshapriya | 2017-04-26 | PASS |  |  | 2017-04-26
96026 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18632 | Functional Features - Querying Functionality - Ability to remove the entire instrument and its series by a click on the close icon of the Instrument label | FUNCTIONAL_FEATURES , QUERY , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | Emergency | Indika Deshapriya | Indika Deshapriya | 2017-04-26 | FAIL | Primary instrument label doesn't have a close icon. Added a comment in Spec 12/5/2017 |  | 2017-04-26
96037 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18633 | Functional Features - Querying Functionality - Overlaying Multiple Instruments | FUNCTIONAL_FEATURES , OVERLAY_OPTIONS , QUERY , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | Emergency | Indika Deshapriya | Indika Deshapriya | 2017-05-08 | WIP |  |  | 2017-04-26
96031 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18634 | Functional Features - Querying Functionality - Overlaying Multiple Instruments - Overlay-ed instrument should be able to add by invoking the Instrument Selector from the 'Add Overlay' filter and selecting another instrument | FUNCTIONAL_FEATURES , OVERLAY_OPTIONS , QUERY , Sample_GRAPH , TC_L3 | Sample Project Client |  | Sample 5.0.0.0.i10 | Emergency | Indika Deshapriya | Indika Deshapriya | 2017-04-28 | FAIL |  | Sample-19330 | 2017-04-26
96045 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18635 | Functional Features - Querying Functionality - Overlaying Multiple Instruments - The instrument label of the overlay-ed instrument should be added to the graph,Labels pane | FUNCTIONAL_FEATURES , OVERLAY_OPTIONS , QUERY , Sample_GRAPH , TC_L3 | Sample Project Client |  | Sample 5.0.0.0.i10 | Not Defined | Indika Deshapriya | Indika Deshapriya | 2017-04-28 | PASS |  |  | 2017-04-26 | Overlay a instrument |  | Instrument label should be added as a label in labels pane right corner | PASS
96041 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18636 | Functional Features - Querying Functionality - Overlaying Multiple Instruments - When Overlaying Multiple Instruments, the color of the instrument trade points should be differentiated | FUNCTIONAL_FEATURES , OVERLAY_OPTIONS , QUERY , Sample_GRAPH , TC_L3 | Sample Project Client |  | Sample 5.0.0.0.i10 | Not Defined | Indika Deshapriya | Indika Deshapriya | 2017-04-28 | FAIL |  |  | 2017-04-26 | Overlay a instrument |  | Trade point colors of primary and Overlayed instrument should be differentiated | PASS
[16 empty] | Overly more than 2 instrument |  | Trade point colors of primary and Overlayed instruments should be differentiated | FAIL
Colors of overlayed instruments trade points should be differentiated
96052 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18637 | Functional Features - Querying Functionality - Overlaying Multiple Instruments - When Overlaying Multiple Instruments, the trade point color coding scheme should be disabled and all trade points should be drawn of the color of their respective instrument | FUNCTIONAL_FEATURES , OVERLAY_OPTIONS , QUERY , Sample_GRAPH , TC_L3 | Sample Project Client |  | Sample 5.0.0.0.i10 | Emergency | Indika Deshapriya | Indika Deshapriya | 2017-04-28 | BLOCKED |  |  | 2017-04-26
96049 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18638 | Functional Features - Querying Functionality - Overlaying Multiple Instruments - Ability to switch on/off the series from toggle option in overlayed instrument label | FUNCTIONAL_FEATURES , OVERLAY_OPTIONS , QUERY , Sample_GRAPH , TC_L3 | Sample Project Client |  | Sample 5.0.0.0.i10 | Not Defined | Indika Deshapriya | Indika Deshapriya | 2017-04-28 | FAIL |  | Sample-19286 | 2017-04-26 | Overlay a instrument |  | This should disable the Overlayed Trade points in Sample graph | PASS | This is a fresh window
Disable Overlayed Trade points using the toggle option in overlay instrument label
[16 empty] | Overlay a instrument |  | This should disable the Overlayed Trade points in Sample graph | FAIL
Clear filters using clear button
Again overlay the same instrument
Disable Overlayed Trade points using the toggle option in overlay instrument label
96076 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18639 | Functional Features - Querying Functionality - Overlaying Multiple Instruments - All series of overlay-ed instruments should be drawn for the query time period of the primary instrument | FUNCTIONAL_FEATURES , OVERLAY_OPTIONS , QUERY , Sample_GRAPH , TC_L3 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-28 | PASS |  |  | 2017-04-26
96069 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18640 | Functional Features - Querying Functionality - Overlaying Multiple Instruments - When the overlayed instrument label is selected it should list down all user selected series in a menu | FUNCTIONAL_FEATURES , OVERLAY_OPTIONS , QUERY , Sample_GRAPH , TC_L3 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-28 | PASS |  |  | 2017-04-26
95966 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18641 | Functional Features - Querying Functionality - Overlaying Multiple Instruments - The color of the primary instrument label and the label of the overlayed instruments should be differentiated | FUNCTIONAL_FEATURES , OVERLAY_OPTIONS , QUERY , Sample_GRAPH , TC_L3 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-27 | FAIL |  |  | 2017-04-26 | Check the color of the primary instrument label and the label of the overlayed instruments |  | The color of the primary instrument label and the label of the overlayed instruments should be differentiated | FAIL
95972 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18643 | Functional Features - Querying Functionality - The legend per instrument for all drawn series should be available in the primary and overlayed instrument label list | FUNCTIONAL_FEATURES , OVERLAY_OPTIONS , QUERY , Sample_GRAPH , TC_L3 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-28 | PASS |  |  | 2017-04-26
95969 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18644 | Functional Features - Querying Functionality - Overlaying Multiple Instruments - Capability to apply filters through the Advanced Filter for Firm, Trader, Client, Price range, Volume range | FUNCTIONAL_FEATURES , OVERLAY_OPTIONS , QUERY , Sample_GRAPH , TC_L3 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-05-08 | FAIL |  |  | 2017-04-26 | Query for an instrument |  |  | PASS
[16 empty] | Check the availability of Firm, Trader, Client, Price range, Volume range filters in Advanced Filters section |  |  | PASS
[16 empty] | Only the Filters mentioned in the spec should be available in advanced filter section |  |  | FAIL | Consideration filter should be removed from advanced filter section
95974 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18645 | Functional Features - Querying Functionality - Overlaying Multiple Instruments - 'Aggressor Side Indication' option should be available in 'Graph Options' | FUNCTIONAL_FEATURES , OVERLAY_OPTIONS , QUERY , Sample_GRAPH , TC_L3 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-28 | FAIL |  |  | 2017-04-26
95980 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18646 | Functional Features - Querying Functionality - Overlaying Multiple Instruments - Any color coding applied over an already existing color coding should overwrite the existing color coding when toggle options turned off | FUNCTIONAL_FEATURES , OVERLAY_OPTIONS , QUERY , Sample_GRAPH , TC_L3 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-28 | BLOCKED |  |  | 2017-04-26
95979 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18647 | Functional Features - Querying Functionality - Overlaying Multiple Instruments - Ability to 'Clear' a query criteria upon which the filters populated will be emptied while the graph container will retain its data | FUNCTIONAL_FEATURES , OVERLAY_OPTIONS , QUERY , Sample_GRAPH , TC_L3 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-05-08 | FAIL |  |  | 2017-04-26 | Query for an instrument |  |  | PASS
[16 empty] | Click on 'clear' button below the duration filter |  | Instrument filter and Duration filter should be emptied while the graph container will retain its data | FAIL | Graph container emptied, when clear button is clicked. As per spec it is wrong
95953 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18653 | Functional Features - Querying Functionality - Overlaying Multiple Instruments - Ability to 'Save Filter' for the specified filter criteria and displayed in the info panel | FUNCTIONAL_FEATURES , OVERLAY_OPTIONS , QUERY , SAVE_FILTER , Sample_GRAPH , TC_L3 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-28 | FAIL | Only the Instrument filter, Date and time saved in 'save filter' |  | 2017-04-26
96244 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18658 | Functional Features - Default Series - The user should be able to select the default options via the drop down menu next to the instrument ID filter field | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L1 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 |  | Indika Deshapriya | 2017-04-26 | PASS |  |  | 2017-04-26
111025 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18659 | Functional Features - Default Series - Ability to view graph points by selecting the option via graph options in which case graph points of all series will be displayed | DEFAULT_SERIES , FUNCTIONAL_FEATURES , GRAPH_OPTIONS , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 |  | Indika Deshapriya | 2017-05-10 | PASS |  |  | 2017-05-03 | graph points of bid series |  |  | PASS
[16 empty] | graph points of offer series |  |  | PASS
96081 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18660 | Functional Features - Default Series - When queries for a particular instrument and a time period, Bid series, Offer series, Trade Points, Traded volume, Trading session, Alerts should be drawn as default series | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-27 | BLOCKED |  | ¦ Sample-19304 | 2017-04-26 | Verify series |  | Bid series drawn | PASS
[18 empty] | Offer series drawn | PASS
[18 empty] | Trade Points drawn | PASS
[18 empty] | Traded volume drawn | PASS
[18 empty] | Trading session drawn | BLOCKED | Not Implemented
[18 empty] | Alerts drawn | PASS
96102 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18661 | Functional Features - Default Series - Bid series should be represented as a step series in the lower area of the graph in a shade of blue for a single instrument query | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-27 | PASS |  |  | 2017-04-26 | Verify Bid series |  | Bid series should be represented as a step series | PASS
[18 empty] | Bid series should be represented in a shade of blue for a single instrument query | PASS
Verify Bid series
96098 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18662 | Functional Features - Default Series - Offer series should be represented as a step series in the upper area of the graph in a shade of red | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-27 | PASS |  |  | 2017-04-26 | Represented as a step series in the upper area of the graph. |  |  | PASS
[16 empty] | The series should be represented in a shade of red. |  |  | PASS
96096 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18663 | Functional Features - Default Series - Trade points should be represented against their trade price and the trade size | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-27 | PASS |  |  | 2017-04-26 |  |  | Trade points should be represented against their trade price | PASS
[16 empty] | CLONE - |  | Trade points should be represented against their trade size | PASS
96114 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18664 | Functional Features - Default Series - Normal single trade should be colour coded as a Red bullet | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-27 | PASS |  |  | 2017-04-26 | Normal single trade |  | Red color bullet | PASS
96116 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18665 | Functional Features - Default Series - Normal single trade cancellations should be colour coded as a Yellow diamond | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-27 | PASS |  |  | 2017-04-26
96111 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18666 | Functional Features - Default Series - Multiple trades/book sweep should be colour coded as a Red bullet with a black outline | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-27 | FAIL | No black outline | Sample-19550 | 2017-04-26
96113 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18667 | Functional Features - Default Series - Multiple trades cancellations should be colour coded as a Yellow diamond with a black outline | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-27 | FAIL | No black outline | Sample-19550 | 2017-04-26
96106 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18668 | Functional Features - Default Series - Single auction trade should be colour coded as a Green bullet | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-27 | FAIL | Not in green bullet | Sample-19550 | 2017-04-26
96109 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18669 | Functional Features - Default Series - Multiple auction trades should be colour coded as Green bullet outlined in black | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-27 | FAIL |  | Sample-19550 | 2017-04-26
96107 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18670 | Functional Features - Default Series - Auction trade cancellations should be colour coded as Yellow diamond with green outline | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-27 | FAIL | No Green Outline | Sample-19550 | 2017-04-26
96104 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18671 | Functional Features - Default Series - Off Book Trades should be colour coded as red bullet with a blue outline | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-27 | FAIL | SELECT trade_report_link_id,instrument_id,transact_time,executed_qty,executed_value,sell_order_id,buy_order_id,sell_client_id,buy_client_id,sell_trader_id,buy_trader_id,sell_broker_id,buy_broker_id,trade_report_id,exec_type,trade_type,trade_sub_type,trade_status,routing_seq,time_sequence,execution_type,buy_participant_name,sell_participant_name,time_sequence AS xvalue,executed_value AS yvalue FROM trade_report WHERE (time_sequence >=4436091408875520 AND time_sequence<=4436095676252160) AND instrument_id='INSCR1803' AND trade_status = 6 | Sample-19552, Sample-19550 | 2017-04-26
Off book trades not visible in SG due to trade status filtering
96120 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18672 | Functional Features - Default Series - Cancelled off book trades should be colour coded as Yellow diamond with a blue outline | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-05-02 | FAIL |  | Sample-19550 | 2017-04-26
96117 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18673 | Functional Features - Default Series - Off book trades should be plotted for Agreed time, Reported time and Transact time | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-05-02 | FAIL |  | Sample-19552 | 2017-04-26
96131 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18674 | Functional Features - Default Series - Trade amendments should be colour coded as Purple bullet | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-05-02 | FAIL |  | Sample-19550 | 2017-04-26
96126 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18675 | Functional Features - Default Series - Filtered out trades should be represented in grey by default | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-05-12 | PASS |  |  | 2017-04-26
96123 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18676 | Functional Features - Default Series - Cross Trades should be colour coded as Red bullet outlined in yellow | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-05-02 | FAIL |  | Sample-19550 | 2017-04-26
96148 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18677 | Functional Features - Default Series - For Trade Amends the price point or the volume bar should be adjusted at the amended transact time | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-05-02 | PASS | New point & vol generated for amended time |  | 2017-04-26
96174 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18678 | Functional Features - Default Series - Trade cancellation should be visible only when the query time period captures the cancellation transact time | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-05-02 | FAIL | Query before cancel shows the same as after cancel. | Sample-19554 | 2017-04-26 | Query before cancellation time |  | Cancellation should not visible & Trade should be dipicted | FAIL
[16 empty] | Query after cancellation |  | Original trade point should not visible & new point for trade cancel should be visible | PASS
96167 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18679 | Functional Features - Default Series - When a user filters out the BOG by a participant, all trade points that does not result from the participant should be colored in grey or removed from the BOG | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-05-12 | PASS |  |  | 2017-04-26 | By default, the grey-out option should be on |  |  | PASS
[16 empty] | all trade points that does not result from the participant should be colored in grey or removed from the BOG |  |  | PASS
96180 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18680 | Functional Features - Default Series - The option in Graph options to color code the trade points based on the participant's state of being Passive or Aggressive on the book When filtering by a participant | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-05-12 | BLOCKED | Clarify? |  | 2017-04-26 | The option should only be enabled when the Sample graph has been filtered by a participant ID |  |  | PASS
[16 empty] | When filter by passive participant | Is Aggressor = Yes | trade point in Red | PASS
[16 empty] | When filter by Aggressive participant | Is Aggressor = Yes | trade point in Green | BLOCKED
[16 empty] | When filter by passive participant | Is Aggressor = No | trade point in ? | UNEXECUTED
[16 empty] | When filter by Aggressive participant | Is Aggressor = No | trade point in ? | UNEXECUTED
96227 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18681 | Functional Features - Default Series - When clicked on a single point of all trade types a call-out box should appear | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-05-03 | BLOCKED |  |  | 2017-04-26 | appear callout box on click |  |  | PASS
[16 empty] | following default fields should be available | Transact time, Buy Client ID |  | FAIL | additional fields available in default view
Executed qty, Sell Client ID
Execute value, Buy Order ID
Buy Firm ID, Sell Order ID
Sell Firm ID, Trade Report ID
Buy Trader ID, Trade Type
Sell Trader ID, Trade Status
[16 empty] | additional fields should be able to add |  |  | PASS
96240 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18682 | Functional Features - Default Series - Trades call-out should enable to click on a certain field of the call-out and highlight all other transactions that equals the same value as that selected field | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-05-03 | FAIL |  | Sample-19556 | 2017-04-26 | Click on Buy Firm ID field and highlight all trades the same Firm ID has participated in the buy side. |  |  | FAIL | No highlighting available
[16 empty] | In this instance all trade points, including any greyed-out points (if any) should be highlighted. |  |  | BLOCKED
96238 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18683 | Functional Features - Default Series - The information to be displayed in the call-out should be user configurable | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-05-03 | FAIL |  | Sample-19558 | 2017-04-26 | By selecting fields from the ‘Select Fields’ pane inside the call out |  | Fields Added to Call-out | PASS
[16 empty] | BY deselecting fields from the ‘Select Fields’ pane inside the call out |  | Fields removed from Call-out | PASS
[16 empty] | The user can add up to a maximum of 16 fields |  |  | FAIL | There are more than 16 fields
96231 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18684 | Functional Features - Default Series - The call out should not be cleared by any user action except when clicked on the close button of the call out | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-05-03 | BLOCKED | This call out box should bind to respective Sample Graph tab/window |  | 2017-04-26
When user switch among other views, this should not interfere
96235 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18685 | Functional Features - Default Series - Ability to navigate back and forth the trade points using the arrow keys | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-05-10 | BLOCKED | failed steps exsits |  | 2017-04-26 | Navigate by < > buttons in visible range |  | should traverse back & forth | PASS
[16 empty] | Navigate by key board arrow keys < > |  | should traverse back & forth | FAIL | Keyboard arrow keys navigates around other few fields inside call out
[16 empty] | Navigate among two points where one is in visible range & other in hidden (zoomed graph) |  | graph should move to the specific trade point by keeping the zoom level (?) | FAIL | call out box dissapears
Call out box should be visible
96234 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18686 | Functional Features - Default Series - The order of the navigation should be according to the transact time | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-05-03 | PASS |  |  | 2017-04-26
96088 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18687 | Functional Features - Default Series - Ability to right click on a trade point and via the context menu, select and highlight any related party transactions | DEFAULT_SERIES , DESCOPED , FUNCTIONAL_FEATURES , INVALID , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-05-03 | BLOCKED | no spec point |  | 2017-04-26
96101 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18688 | Functional Features - Default Series - When clicked on the multiple trade point, the tool tip information should be available for all trade points | DEFAULT_SERIES , FUNCTIONAL_FEATURES , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-05-03 | PASS |  |  | 2017-04-26 | When clicked on the multiple trade point |  | tool tip information should be available for all trade points | PASS
[16 empty] | The user should be able to navigate between tool tips using arrow keys |  |  | PASS | UI <> buttons
[16 empty] | No any conflicts when overlap among same trade points |  |  | PASS
111013 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18689 | Functional Features - Default Series - Ability to invoke Trades window by clicking on the Trades Window button inside the call out | DEFAULT_SERIES , FUNCTIONAL_FEATURES , INVOKING_OPTIONS , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 |  | Indika Deshapriya | 2017-05-03 | FAIL |  | Sample-19579 | 2017-05-03 | Tool Tip available for invoke trade window |  |  | FAIL
[16 empty] | invoke Trades window by clicking on the Trades Window button |  |  | PASS
[16 empty] | Call out should not disappear after invoking trade window |  |  | FAIL | call out disappeared on returning to SG
[16 empty] | Should only allow to invoke 5 trade views |  |  | FAIL | FE crash on invoking 6th
[16 empty] | user should be able to invoke Trades window with relevant trade details by clicking on the Trades Window button inside the call out. |  |  | UNEXECUTED
[16 empty] | If there are more than one trade at a particular point, all trades in that point should be listed in the trades window. |  |  | PASS
95967 | SampleGraph_Manual_Test_Cycle-1.0.p1 | Sample-18689 | Functional Features - Default Series - Ability to invoke Trades window by clicking on the Trades Window button inside the call out | DEFAULT_SERIES , FUNCTIONAL_FEATURES , INVOKING_OPTIONS , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 | Indika Deshapriya | Indika Deshapriya | 2017-04-28 | PASS | Trades window invoked. data in Trades window not verified |  | 2017-04-26 | Tool Tip available for invoke trade window |  |  | UNEXECUTED
[16 empty] | invoke Trades window by clicking on the Trades Window button |  |  | UNEXECUTED
[16 empty] | Call out should not disappear after invoking trade window |  |  | UNEXECUTED
[16 empty] | Should only allow to invoke 5 trade views |  |  | UNEXECUTED
[16 empty] | user should be able to invoke Trades window with relevant trade details by clicking on the Trades Window button inside the call out. |  |  | UNEXECUTED
[16 empty] | If there are more than one trade at a particular point, all trades in that point should be listed in the trades window. |  |  | UNEXECUTED
111023 | SampleGraph_Manual_Test_Cycle-1.0.p2 | Sample-18690 | Functional Features - Default Series -'Size trades from volume' mode option in Graph Options availability | DEFAULT_SERIES , FUNCTIONAL_FEATURES , GRAPH_OPTIONS , Sample_GRAPH , TC_L2 | Sample Project Client |  | Sample 5.0.0.0.i10 | 5 |  | Indika Deshapriya | 2017-05-03 | BLOCKED |  |  | 2017-05-03 | The size assigned to the trade point will depend on the distribution of the trade volumes (data set) of the user defined query |  |  | PASS
[16 empty] | The data set (trade volumes) should be segregated into ranges and the respective sizes should be assigned |  |  | PASS
[16 empty] | The sizes of the bubbles should be determined as follows: |  |  | PASS
The system should have a maximum and a minimum size pre-defined which will be used as the two standard extremes.
The data set should be broken down into a set of ranges.
The two extreme sizes will be used as benchmarks to determine the intermediary sizes depending on the number of ranges available.
When assigning the size, the smallest size should be assigned to the minimum range and the largest size to the maximum range.
[16 empty] | This should be exposed as a mode for the user in Graph Options. |  |  | FAIL | Graph Options not available on
Releases\5.0.0.0.i11\Release-2017-05-02-06.10PM_clean
[16 empty] | When enabled in Graph Options. |  | sizes of trade point should be proportionate to trade size | PASS
[16 empty] | When disabled in Graph Options. |  | sizes of trade point should be same for all trade sizes | PASS
[16 empty] | By default Normal mode should be on |  |  | FAIL
Note on E6: Deshapriya, Indika: Functionalities not yet available in the current implementation